## Sheet1
Timeline (13 weeks, May 4 – Jul 31, 2026)
Track / Task | Owner | Hours | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
|  |  | May 04 | May 11 | May 18 | May 25 | Jun 01 | Jun 08 | Jun 15 | Jun 22 | Jun 29 | Jul 06 | Jul 13 | Jul 20 | Jul 27 |  | Total Hours | Rate | Total Cost
FOUNDATIONS | [15 empty] | Kevin | 167 | 90000 | 15030000
Data Handling (ScriptableObject-driven) | Kevin | 4 | W1 May 04: 4 | Syafira | 60 | 75000 | 4500000
Common interaction event interface + Interaction System (Start, Play, End System) | Kevin | 12 | W1 May 04: 8 | Total | 227 |  | 19530000
Refactor save system | Kevin | 2 | W1 May 04: 2
Animator Controller templates | Kevin | 2 | W1 May 04: 2
Asset audit, prefab pivot/socket review for glassware | Syafira | 10 | W1 May 04: 10
INTERACTION
Drag-and-snap primitive.(scenes (4–9)) | Kevin | 8 | W2 May 11: 8
Drag with auto-rotate-in-zone (Buret rinse ) | Kevin | 5 | W3 May 18: 5
Refactor pan-rotate-scale | Kevin | 8 | W2 May 11: 8
Pinch-zoom (Camera Zoom) on burette | Kevin | 6 | W3 May 18: 6
Pull/Drag-detach (Indicator scenes (sc.9 / sc.8 Komplek)) | Kevin | 4 | W3 May 18: 4
Circular swirl gesture detector (Erlenmeyer mixing) | Kevin | 6 | W3 May 18: 6
Glassware base anim library (drag, attach, pour) | Syafira | 5 | W3 May 18: 5
Buret prep clips (BA-4 + K-4 + EDTA rinse) | Syafira | 5 | W3 May 18: 5
BEBAS AIR SCENES (1-12)
BA-4 Buret prep (7 steps) | Kevin | 7 | W4 May 25: 7
BA-5 Baku primer (4 steps) | Syafira | 6 | W4 May 25: 6
BA-6 Blanko (6 steps) | Kevin | 8 | W5 Jun 01: 8
BA-7 Penimbangan (3 steps) | Syafira | 3 | W4 May 25: 3
BA-8 Larutan sampel (6 steps) | Kevin | 9 | W5 Jun 01: 9
BA-9 Indikator (4 steps, ×3 Erlenmeyers) | Syafira | 7 | W6 Jun 08: 7
BA-10/11/12 Pembakuan + Blanko + Sampel triplo | Kevin | 9 | W6 Jun 08: 9
BA scene clips: 5/6/7/8/9 (pour, attach, swirl, drop) | Syafira | 22 | W7 Jun 15: 22
BA scene clips: 10/11/12 (5 mL drop, triplo) | Syafira | 8 | W8 Jun 22: 8
KOMPLEKSOMETRI SCENES (1-12)
K-4 Buret prep (6 steps) | Kevin | 8 | W6 Jun 08: 8
K-5 Baku primer (10 steps) | Kevin | 12 | W7 Jun 15: 12
K-6 Blanko (6 steps) | Syafira | 9 | W7 Jun 15: 9
K-7 Penimbangan (3 steps) | Syafira | 3 | W8 Jun 22: 3
K-8 Larutan sampel (7 steps) | Kevin | 9 | W8 Jun 22: 9
K-9 Indikator + color transition wiring | Kevin | 4 | W9 Jun 29: 4
K-10/11/12 Titrasi triplo & blanko | Kevin | 6 | W8 Jun 22: 6
K scene clips: 5/6/7 | Syafira | 2 | W9 Jun 29: 2
K scene clips: 8/9/10/11/12 + Komplek anim controllers | Syafira | 2 | W10 Jul 06: 2
INTEGRATION, POLISH & QA
Bug-fix, Polishing, Full regression playthrough (both titrations × all scenes) | Kevin | 32 | W9 Jun 29: 8; W10 Jul 06: 8; W11 Jul 13: 8; W12 Jul 20: 8
Final clip revisions, Animator polish | Syafira | 5 | W12 Jul 20: 5
Build Android + Bug Buffer | Kevin | 6 | W9 Jun 29: 3; W10 Jul 06: 3
Documentation | Kevin | 2 | W12 Jul 20: 2
WEEKLY TOTALS (h) | P / A | 256 | 26 | 16 | 31 | 16 | 17 | 24 | 43 | 26 | 17 | 13 | 8 | 13 | 0